## Sheet1
SPRINT # | TASK ID | TASK NAME | ASSIGNED TO | START | FINISH | SPRINT READY | PRIORITY | STATUS | ASSIGNED TO SPRINT | Subtask | Challenges
Sprint 1 | T001 | Wireframe | Vansh Aggarwal, Yanish, Raunit | 2023-02-07 | 2023-02-08 | Yes | High | Complete | Yes | Refining Content Structure | None
| T002 | Architecture Design, | Pooja, Vishal Srivastav | 2023-02-10 | 2023-02-12 | Yes | High | Complete | Yes | Understanding of Requirements | Finalising the best architecture desing to incorporate our design needs
| T003 | Database Model | Pooja, Vishal Srivastav | 2023-02-08 | 2023-02-10 | Yes | High | Complete | Yes | Mappings Between Tables | Incorporating Many to many relation between user and project in JAVA JPA
| T004 | Feasibility study | All member | 2023-02-06 | 2023-02-09 | Yes | High | Complete | Yes | Finalized the tech stack | None
Sprint 2 | T005 | Frontend Design | Vansh Aggarwal, Vishal Srivastav, Rishu | 2023-02-13 | 2023-02-19 | Yes | Medium | Complete | Yes | Navigation bar Profiles Manager Request Tab User Details and avatar Status Cards | Responsivness
| T006 | API's | Pooja | 2023-02-14 | 2023-02-19 | Yes | High | In Progress | Yes | User Details Resource reqeust Manager reqeusts (Entities, Repo, Dto, Controller, Service) | None
| T007 | User Authentication | Vishal Srivastav, Raunit, Keshav | 2023-02-13 | 2023-02-19 | Yes | High | Complete | Yes | Token creation Token authorization Token configuration | None
| T008 | Testing | Rudraksh | 2023-02-16 | 2023-02-19 | Yes | Medium | Complete | Yes | Finalising Manual Test Cases | None
Sprint 3 | T09 | Backend-Frontend Integration | Vishal Srivastav | 2023-02-20 | 2023-02-22 | Yes | High | Complete | Yes | NA | None
| T10 | Frontend Features | Vansh Aggarwal, Rishu | 2023-02-22 | 2023-02-25 | Yes | High | Complete | Yes | Request change log Notification Table filter & search | Finding suited library to incoporate our needs
| T11 | API's | Pooja | 2023-02-20 | 2023-02-23 | Yes | High | In Progress | Yes | User Details Resource reqeust Manager reqeusts (Entities, Repo, Dto, Controller, Service) | None
| T12 | Backend Features | Vishal Srivastav,Pooja | 2023-02-24 | 2023-02-26 | Yes | High | Complete | Yes | Request change log Mail service | Modification of Schema to incoporate logs
| T13 | Testing | Rudraksh | 2023-02-23 | 2023-02-26 | Yes | High | Complete | Yes | Integration testing System Testing UI functional testing | Managing popups and security scans while browsing automation
Sprint 4 | T014 | Presentation | All | 2023-02-27 | 2023-02-25 | Yes | High | Complete | Yes | Presentation Scripts | Synchronization
| T015 | Add on Features | Vishal | 2023-02-27 | 2023-02-22 | Yes | High | Complete | Yes | Analytics | None
| T016 | Testing | Rudraksh | 2023-03-01 | 2023-03-04 | Yes | High | Complete | Yes | Sonar cloud integration Final test reports creation | Automating Sonar scan